## All Mechanical
| ITEMS | Teams Costs | FB Engineering Costs | RJ Mechanical Costs | Agile Costs | Comments
1 | Preliminaries, including Health & Safety and working/manufacturing drawings. | 32824 | 43947 | 35394 | 3206.25 | FB Engineering are a little high on this element of the works
2 | Site Set-up. | 2750 | 3589 | 4890 | Included In 1
3 | Mechanical Services
3.1 | New Boiler Plant & pipework installation | 32675 | 34167 | 37582 | 37968.75
3.2 | New Pressurisation Unit and Expansion Vessel | 2831 | 4551 | 3311 | 2869.87
3.3 | New DHW Generator & pipework installation | 45840 | 32417 | 23417 | 16219.12 | Teams cost is high in this area but is low in item 3.12, we contacted them regarding this matter and they have confirmed that they have items in 3.3 which poosible should have been in 3.12, but overall they are still a bit high but nothing to much
3.4 | New Radiators. Ground floor & pipework installation | 38482 | 41798 | 46547 | 45897.75
3.5 | New Radiators First floor & pipework installation | 35879 | 40499 | 43218 | 38811.37
3.6 | New Radiators Second Floor & pipework installation | 17376 | 15947 | 16783 | 16815.37
3.7 | Heating Circulation Pumps | 9740 | 7562 | 8978 | 6725.25
3.8 | Boiler Plant Controls and field wiring | 66470 | 72150 | 69750 | 63641.25
3.9 | Heating and Comfort Cooling including field wiring. | 120275 | 139500 | 131786 | 107156.25 | Teams cost looks is low but we have contacted them and they have confirmed they are all compliant.
3.1 | New gas service | 5875 | 7490 | 9790 | 7059.37
3.11 | New MCWS | 9749 | 10749 | 13657 | 39920.62
3.12 | New Domestic Water services | 35891 | 44264 | 42578 | Included in above
3.13 | New above ground drainage. | 24440 | 21370 | 18750 | 19687.5
3.14 | New Mechanical Ventilation installation | 61775 | 64288 | 59743 | 79074
3.15 | New local ventilation extraction fans | 12759 | 16620 | 14620 | 5197.5
3.16 | Pipework thermal insulation | 9364 | 14486 | 10874 | 11238.75
3.17 | Ventilation thermal insulation | 11289 | 9188 | 14654 | 9774
3.18 | Demonstration of equipment | 1750 | 1950 | 1240 | Included in 1
3.19 | Testing and commissioning | 8129 | 5930 | 6750 | 5346
3.2 | As fitted drawings | 950 | 2275 | 1570 | Included in 1
3.21 | Operation and maintenance manuals | 1500 | 2100 | 1250 | Included in 1
3.22 | Any items not mentioned above (contractor to list below) | 15634 | 18750 | 7467 | 17437.5 | RJ Mechanical are low on this item, we have contacted them, and it has been confirmed that they have not included for the leak-detection, which came out post tender. We would suggest adding a sum of approx. £ 10,000.00 to make there bid inline with the others
| Grand total of Mechanical services | 604247 | 655587 | 624599 | 534046.47
NOTE: | 1. Generally all items which have not got a comment by them are within expected variances for the activities
2. We have contacted all three contractors for further discount and they have all confirmed that this is the best cost they can provide due to the complexity of the mechanical installation.

## Agile
AGILE | Costs
Preliminaries, including Health & Safety and working/manufacturing drawings. | 23750
Site Set-up. | 600
Electrical Services
New LV main panel installation | 11022.99
New sub main distribution switchgear installation | 9858.75
New sub main cabling installation to Distribution Boards | 15572.38
New sub main cabling/DB installation to pharmacy | 1826.82
New sub main cabling/DB installation to Optometrist | 2623.14
Internal luminaries – Phi Lighting | 101011.37
New lighting and emergency lighting installation (inc controls) | 55900.16
External luminaries – Candela lighting | 20258.7
External lighting installation | 3402
External power installation | Included in 3.11
New small power installation | 30195.73
Data installation works | 22932
TV System installation works | 761.25
Secondary containment installation | 8498.64
New Dado trunking installation | 4576.33
Disabled Toilet alarm installation | 1098
New intruder alarm/CCTV/Panic attack alarm power requirements installation | 1045.8
New Fire alarm power requirements installation | 189.24
New power supplies to mechanical services | 3556.04
Induction loops supply and installation | 900
Earthing and bonding | 470.64
Demonstration of equipment | 420
Testing and commissioning | 1800
As fitted drawings | 1200
Operation and maintenance manuals | 600
Any items not mentioned above (contractor to list below)
Total | 324069.98

## Tender offer
Note: |  | All figures for value engineered costs are only estermated at this time, more accurate cost can be give when the VE options are compaired for compliance
Compliant tender offer ( separate M&E contractors )
Mechanical: |  | 604247 |  | This is a totally compliant bid for both disciplines
Electrical: |  | 324069
Total: |  | 928316
Value engineering offer ( separate M&E contractors )
Mechanical: |  | 595247 |  | This would be achieved by changing the VRF equipment and the DHW boilers for different make ( compliance must be checked for design and BREAME points )
Electrical: |  | 316569 |  | This would be achieved by changing the specified light fitting for both inside and outside ( compliance must be checked for design, photometric and looks )
Total: |  | 911816
Compliant tender offer ( Combined M&E contractor )
Mechanical: |  | 604247 |  | This is a totally compliant bid for both disciplines
Electrical: |  | 324069
Saving |  | -20000 |  | This would be achieved by the reduction of prelims, as management costs would be reduced. This can only be given if the contract is placed direct with Agile by Revelan
( due to the complexity of this project it would be prudent to have an M&E combined bid as any unforeseen problems would be spotted a lot earlier by one project manager )
Total: |  | 908316
Value engineering offer ( Combined M&E contractor )
Mechanical: |  | 595247 |  | This would be achieved by changing the VRF equipment and the DHW boilers for different make ( compliance must be checked for design and BREAME points )
Electrical: |  | 316569 |  | This would be achieved by changing the specified light fitting for both inside and outside ( compliance must be checked for design, photometric and looks )
Saving |  | -20000 |  | This would be achieved by the reduction of prelims, as management costs would be reduced.
( due to the complexity of this project it would be prudent to have an M&E combined bid as any unforeseen problems would be spotted a lot earlier by one project manager )
Total: |  | 891816
Note: | 1 | None of the above Electrical costs include the Fire Alarm, CCTV, Access Control, Panic Attack and Intruder costs from nominated contractor ( CBS ), the costs for these disciplines area as follows
|  |  | Fire Alarm: |  | 24896
|  |  | CCTV: |  | 34310
|  |  | Access Control: |  | 36946 | This does not include the electric gates & Car park barrier
|  |  | Intruder: |  | 7318
|  |  | Panic Attack: |  | 15956
|  |  | Total: |  | 119426
| 2 | Alternative costs the Fire Alarm, CCTV, Access Control, Panic Attack and Intruder costs from Direct Security Systems, the costs for these disciplines area as follows
|  |  | Fire Alarm: |  | 18995
|  |  | CCTV: |  | 23150
|  |  | Access Control: |  | 32150 | This does not include the electric gates & Car park barrier
|  |  | Intruder: |  | 8775
|  |  | Panic Attack: |  | 6495
|  |  | Total: |  | 89565
| 3 | None of the above Mechanical costs include the supply and fitting of sanitary ware ( this includes taps, sinks, toilets, cleaners sinks etc. ). A cost can be give if required
Total cost of value engineered project using one M&E contractor ( including alternative specialist contractor ):
Mechanical: |  | 595247
Electrical: |  | 316569
Saving |  | -20000
Specialist |  | 89565 | This does not include the electric gates & Car park barrier
Total: |  | 981381
Total budget cost allowed for at initial cost plan stage
Mechanical: |  | 521027.81
Electrical: |  | 346892.29 |  | ( Including specialist contractor & car park lighting )
Total: |  | 867920.1
Deficit amount between Budget and actual VE option |  |  |  | ( Using alternative specialist contractors )
Total: |  | 113460.9